## Sprint 1 - Burndown Chart
Navigo - Sprint 1 - Burndown Chart
Tasks | Working Hours | 2020-01-30 | 2020-02-01 | 2020-02-03 | 2020-02-05 | 2020-02-07 | 2020-02-09 | 2020-02-11 | 2020-02-13 | 2020-02-26 | 2020-02-27 | End Hours
Project Selection and Project Approval | 10 | 1 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 10
Brainstorming and Requirement Gathering | 24 | 6 | 4 | 2 | 2 | 4 | 3 | 2 | 1 | 0 | 0 | 24
Presentation for deliverable 1 | 5 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 5
Peer to Peer 1 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Actual Remaining Hours | 40 | 33 | 28 | 24 | 20 | 15 | 8 | 4 | 1 | 0 | 0
Estimated Remaining hours | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team Member
Tasks | Priya | 2020-01-30: Sunil; 2020-02-01: Karthik; 2020-02-03: Bharath; 2020-02-05: Pranav; 2020-02-07: Rahul
Project Selection and Project Approval | 1.5 | 2020-01-30: 3; 2020-02-01: 2; 2020-02-03: 1.5; 2020-02-05: 1; 2020-02-07: 1
Brainstorming and Requirement Gathering | 5 | 2020-01-30: 4; 2020-02-01: 4.5; 2020-02-03: 4.5; 2020-02-05: 3; 2020-02-07: 3
Presentation for deliverable 1 | 2 | 2020-01-30: 0; 2020-02-01: 2; 2020-02-03: 1; 2020-02-05: 0; 2020-02-07: 0
Peer to Peer 1 Review | 1 | 2020-01-30: 0; 2020-02-01: 0; 2020-02-03: 0; 2020-02-05: 0; 2020-02-07: 0
End Hours | 9.5 | 2020-01-30: 7; 2020-02-01: 8.5; 2020-02-03: 7; 2020-02-05: 4; 2020-02-07: 4
Cap Stone Project
Project1 |  | 2020-01-30: Project2
Tasks | Kartik | 2020-01-30: Task
Project Selection and Project Approval | 2 | 2020-01-30: Jira Updates; 2020-02-01: 2
Brainstorming and Requirement Gathering | 4.5 | 2020-01-30: PPT; 2020-02-01: 3
Presentation for deliverable 1 | 2 | 2020-01-30: Chatbot/Testing; 2020-02-01: 0
Peer to Peer 1 Review | 0 | 2020-01-30: Peer to Peer 1 Review; 2020-02-01: 1
Feedback | 2 | 2020-01-30: Feedback; 2020-02-01: 2
Sprint1 | 8 | 2020-01-30: Sprint 1; 2020-02-01: 7
Technology assessment, Prep for Sprint 2, Signup and login | 1.5 | 2020-01-30: Search Bar Implementation; 2020-02-01: 2
Created a AWS Account, rokognition and lexa | 0 | 2020-01-30: JIRA Updates; 2020-02-01: 2
New York Location Research and Product backlog | 0.5 | 2020-01-30: Navigo testing; 2020-02-01: 0
GitHub | 0.5 | 2020-01-30: Github; 2020-02-01: 1
Presentation for deliverable 2 | 0 | 2020-01-30: Sprint 2 PPT; 2020-02-01: 3
Brainstroming on database | 1 | 2020-01-30: Brainstorm on Sprint 3; 2020-02-01: 1
Peer to Peer 2 Review | 1 | 2020-01-30: Peer to Peer 2 Review; 2020-02-01: 1
Feedback | 2 | 2020-01-30: Feedback; 2020-02-01: 8
Sprint2 | 4.5 | 2020-01-30: Sprint2
Research on Technical[IEEE] paper and studying formats | 0.5 | 2020-01-30: Tech Paper research/updates; 2020-02-01: 1
Researched and Added Literature review | 0 | 2020-01-30: Sprint 3 updates; 2020-02-01: 0.5
Abstract, Introduction, added Project Requirement | 0.5 | 2020-01-30: JIRA updates; 2020-02-01: 1
Database Schema/Documentation format | 0 | 2020-01-30: Github; 2020-02-01: 0
System Diagrams, ER Diagrams, Data Modeling | 0 | 2020-01-30: Manual Testing; 2020-02-01: 0
Conclusion, Discussion, Summary and References | 1 | 2020-01-30: Database Connectivity; 2020-02-01: 0
Submission of deliverable 3[Technical paper] | 0.25 | 2020-01-30: Submission of Deliverable 3; 2020-02-01: 0.25
brainstorm/coding - Home Page | 0.5 | 2020-01-30: Brainstorm on Sprint 4; 2020-02-01: 2
Peer to Peer 3 Review | 1 | 2020-01-30: Peer to Peer 3 Review; 2020-02-01: 1
Feedback | 2.5 | 2020-01-30: Feedback; 2020-02-01: 1
Sprint 3 | 4.5 | 2020-01-30: Sprint 3; 2020-02-01: 8
Product backlog/Documentation update | 1.5 | 2020-01-30: Designing and Implementing NavigoMerch store; 2020-02-01: 3
Wiki page: Code, Techhnology tools and Project Management | 0.5 | 2020-01-30: Coding- Merch Store; 2020-02-01: 4
Wiki page: Architecture and Design, Burndown Charts, Demo | 0 | 2020-01-30: Architecture/Design; 2020-02-01: 1
coding - Home Page, About Us, Contact | 0 | 2020-01-30: Github; 2020-02-01: 1
coding - User Signup and Login | 0 | 2020-01-30: Final JIRA Updates; 2020-02-01: 0.25
Manual Testing | 0 | 2020-01-30: Manual Testing; 2020-02-01: 0.5
Draft document on design and technologies | 0 | 2020-01-30: Sprint 4 PPT; 2020-02-01: 5
Sprint 4 documentation | 2 | 2020-01-30: Final Documentation; 2020-02-01: 2
Retrospective documentation/mvp | 1 | 2020-01-30: Final Retro; 2020-02-01: 1
Peer to Peer 4 Review | 1 | 2020-01-30: Peer to Peer 4 Review
Feedback | 3 | 2020-01-30: Feedback; 2020-02-01: 1
Sprint 4 | 5 | 2020-01-30: Sprint 4

## Sprint 2 - Burndown Chart
Navigo - Sprint 2 - Burndown Chart
Tasks | Working Hours | 2020-02-28 | 2020-03-01 | 2020-03-03 | 2020-03-05 | 2020-03-07 | 2020-03-09 | 2020-03-11 | 2020-03-13 | 2020-03-25 | 2020-03-26 | End Hours
Technology assessment, Prep for Sprint 2, Signup and login | 10.5 | 1 | 2 | 2.5 | 0.5 | 2 | 1 | 0 | 1.5 | 0 | 0 | 10.5
Created a AWS Account, rokognition and lexa | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
New York Location Research and Product backlog | 3.5 | 1 | 1 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 3.5
GitHub | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4
Presentation for deliverable 2 | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 3
Brainstroming on database | 8.5 | 0.5 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 8.5
Peer to Peer 2 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Actual Remaining Hours | 31 | 27.5 | 23.5 | 19 | 17 | 12.5 | 7.5 | 5.5 | 1 | 0 | 0
Estimated Remaining hours | 31 | 27.9 | 24.8 | 21.7 | 18.6 | 15.5 | 12.4 | 9.3 | 6.2 | 3.1 | -4.4409e-15
Team Member
Tasks | Priya | 2020-02-28: Sunil; 2020-03-01: Karthik; 2020-03-03: Bharath; 2020-03-05: Pranav; 2020-03-07: Rahul
Technology assessment, Prep for Sprint 2, Signup and login | 2 | 2020-02-28: 3; 2020-03-01: 1.5; 2020-03-03: 1; 2020-03-05: 2.5; 2020-03-07: 3
Created a AWS Account, rokognition and lexa | 0 | 2020-02-28: 0.5; 2020-03-01: 0; 2020-03-03: 0; 2020-03-05: 0; 2020-03-07: 0
New York Location Research and Product backlog | 1 | 2020-02-28: 0.5; 2020-03-01: 0.5; 2020-03-03: 1; 2020-03-05: 0.5; 2020-03-07: 2
GitHub | 0.5 | 2020-02-28: 0.5; 2020-03-01: 0.5; 2020-03-03: 1.5; 2020-03-05: 0.5; 2020-03-07: 0.5
Presentation for deliverable 2 | 0.5 | 2020-02-28: 0.5; 2020-03-01: 1; 2020-03-03: 0.5; 2020-03-05: 0.5; 2020-03-07: 1
Brainstroming on database | 2.5 | 2020-02-28: 1.5; 2020-03-01: 1; 2020-03-03: 0.5; 2020-03-05: 2; 2020-03-07: 1
Peer to Peer 2 Review | 1 | 2020-02-28: 0; 2020-03-01: 0; 2020-03-03: 0; 2020-03-05: 0; 2020-03-07: 0
End Hours | 7.5 | 2020-02-28: 6.5; 2020-03-01: 4.5; 2020-03-03: 4.5; 2020-03-05: 6; 2020-03-07: 7.5

## Sprint 3 - Burndown Chart
Navigo - Sprint 3 - Burndown Chart
Tasks | Working Hours | 2020-03-27 | 2020-03-29 | 2020-03-31 | 2020-04-02 | 2020-04-04 | 2020-04-06 | 2020-04-08 | 2020-04-10 | 2020-04-22 | 2020-04-23 | End Hours
Research on Technical[IEEE] paper and studying formats | 3 | 1 | 0.5 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 3
Researched and Added Literature review | 3 | 0.5 | 0.5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3
Abstract, Introduction, added Project Requirement | 1.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 1.5
Database Schema/Documentation format | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2
System Diagrams, ER Diagrams, Data Modeling | 2 | 0 | 0.5 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
Conclusion, Discussion, Summary and References | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
Submission of deliverable 3[Technical paper] | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 1.5
brainstorm/coding - Home Page | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5 | 0 | 0 | 5.5
Peer to Peer 3 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Actual Remaining Hours | 21.5 | 19.5 | 16.5 | 14 | 12 | 8 | 6 | 3.5 | 1 | 0 | 0
Estimated Remaining hours | 21.5 | 19.35 | 17.2 | 15.05 | 12.9 | 10.75 | 8.6 | 6.45 | 4.3 | 2.15 | 0
Team Member
Tasks | Priya | 2020-03-27: Sunil; 2020-03-29: Karthik; 2020-03-31: Bharath; 2020-04-02: Pranav; 2020-04-04: Rahul
Research on Technical[IEEE] paper and studying formats | 0.5 | 2020-03-27: 0.5; 2020-03-29: 0.5; 2020-03-31: 0.5; 2020-04-02: 0.5; 2020-04-04: 0.5
Researched and Added Literature review | 1 | 2020-03-27: 0; 2020-03-29: 0; 2020-03-31: 0; 2020-04-02: 0.5; 2020-04-04: 1.5
Abstract, Introduction, added Project Requirement | 0.5 | 2020-03-27: 0; 2020-03-29: 0.5; 2020-03-31: 0; 2020-04-02: 0.5; 2020-04-04: 0
Database Schema/Documentation format | 0 | 2020-03-27: 1; 2020-03-29: 0; 2020-03-31: 0; 2020-04-02: 1; 2020-04-04: 0
System Diagrams, ER Diagrams, Data Modeling | 0 | 2020-03-27: 0; 2020-03-29: 1; 2020-03-31: 1; 2020-04-02: 0; 2020-04-04: 0
Conclusion, Discussion, Summary and References | 0.5 | 2020-03-27: 0; 2020-03-29: 1.5; 2020-03-31: 0; 2020-04-02: 0; 2020-04-04: 0
Submission of deliverable 3[Technical paper] | 0.25 | 2020-03-27: 0.25; 2020-03-29: 0.25; 2020-03-31: 0.25; 2020-04-02: 0.25; 2020-04-04: 0.25
brainstorm/coding - Home Page | 0.5 | 2020-03-27: 3.5; 2020-03-29: 0.5; 2020-03-31: 0.5; 2020-04-02: 0.5; 2020-04-04: 0
Peer to Peer 3 Review | 1 | 2020-03-27: 0; 2020-03-29: 0; 2020-03-31: 0; 2020-04-02: 0; 2020-04-04: 0
End Hours | 4.25 | 2020-03-27: 5.25; 2020-03-29: 4.25; 2020-03-31: 2.25; 2020-04-02: 3.25; 2020-04-04: 2.25

## Sprint 4 - Burndown Chart
Navigo - Sprint 4 - Burndown Chart
Tasks | Working Hours | 2020-04-24 | 2020-04-26 | 2020-04-28 | 2020-04-30 | 2020-05-02 | 2020-05-04 | 2020-05-06 | 2020-05-08 | 2020-05-13 | 2020-05-14 | End Hours
Product backlog/Documentation update | 5.5 | 1 | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5
Wiki page: Code, Techhnology tools and Project Management | 5 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 5
Wiki page: Architecture and Design, Burndown Charts, Demo | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
coding - Home Page, About Us, Contact | 12 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 12
coding - User Signup and Login | 12.5 | 1 | 1 | 1 | 2 | 0.5 | 3 | 2 | 2 | 0 | 0 | 12.5
Manual Testing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Draft document on design and technologies | 5 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 5
Sprint 4 documentation | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 0 | 0 | 6
Retrospective documentation/mvp | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2
Peer to Peer 4 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Actual Remaining Hours | 52 | 50 | 45 | 39.5 | 35.5 | 28 | 20.5 | 12 | 1 | 1 | 0
Estimated Remaining hours | 52 | 46.8 | 41.6 | 36.4 | 31.2 | 26 | 20.8 | 15.6 | 10.4 | 5.2 | 0
Team Members
Tasks | Priya | 2020-04-24: Sunil; 2020-04-26: Karthik; 2020-04-28: Bharath; 2020-04-30: Pranav; 2020-05-02: Rahul
Product backlog/Documentation update | 1 | 2020-04-24: 1; 2020-04-26: 1.5; 2020-04-28: 1; 2020-04-30: 1; 2020-05-02: 0
Wiki page: Code, Techhnology tools and Project Management | 1 | 2020-04-24: 2.5; 2020-04-26: 0.5; 2020-04-28: 0; 2020-04-30: 1; 2020-05-02: 0
Wiki page: Architecture and Design, Burndown Charts, Demo | 0 | 2020-04-24: 2; 2020-04-26: 0; 2020-04-28: 0; 2020-04-30: 0; 2020-05-02: 0
coding - Home Page, About Us, Contact | 0 | 2020-04-24: 7; 2020-04-26: 0; 2020-04-28: 2; 2020-04-30: 0; 2020-05-02: 3
coding - User Signup and Login | 0 | 2020-04-24: 9.5; 2020-04-26: 0; 2020-04-28: 0; 2020-04-30: 0; 2020-05-02: 3
Manual Testing | 0 | 2020-04-24: 0; 2020-04-26: 0; 2020-04-28: 0; 2020-04-30: 1; 2020-05-02: 0
Draft document on design and technologies | 2 | 2020-04-24: 1; 2020-04-26: 0; 2020-04-28: 1; 2020-04-30: 1; 2020-05-02: 0
Sprint 4 documentation | 1 | 2020-04-24: 0; 2020-04-26: 2; 2020-04-28: 1.5; 2020-04-30: 1.5; 2020-05-02: 0
Retrospective documentation/mvp | 0 | 2020-04-24: 1; 2020-04-26: 1; 2020-04-28: 0; 2020-04-30: 0; 2020-05-02: 0
Peer to Peer 3 Review | 1 | 2020-04-24: 0; 2020-04-26: 0; 2020-04-28: 0; 2020-04-30: 0; 2020-05-02: 0
End Hours | 5 | 2020-04-24: 24; 2020-04-26: 5; 2020-04-28: 5.5; 2020-04-30: 5.5; 2020-05-02: 6