## Sprint 1 - Burndown Chart
CS 692: Navigo - Sprint 1 - Burndown Chart
Tasks | Working Hours | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | End Hours
Jira Updates | 10 | 1 | 1 | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 8
Sprint 1 PPT/Presentation | 24 | 5 | 4 | 3 | 1 | 4 | 3 | 1 | 1 | 0 | 0 | 22
Chatbot & Testing | 5 | 1 | 1 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 5
Peer to Peer 1 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Actual Remaining Hours | 40 | 33 | 27 | 23 | 21 | 16 | 10.5 | 7.5 | 5 | 4 | 4
Estimated Remaining hours | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Cap Stone Project
Project1 |  | 2020-08-24: Project2
Tasks | Kartik | 2020-08-24: Task
Project Selection and Project Approval | 2 | 2020-08-24: Jira Updates; 2020-08-25: 2
Brainstorming and Requirement Gathering | 4.5 | 2020-08-24: PPT; 2020-08-25: 3
Presentation for deliverable 1 | 2 | 2020-08-24: Chatbot/Testing; 2020-08-25: 0
Peer to Peer 1 Review | 0 | 2020-08-24: Peer to Peer 1 Review; 2020-08-25: 1
Feedback | 2 | 2020-08-24: Feedback; 2020-08-25: 2
Sprint1 | 8 | 2020-08-24: Sprint 1; 2020-08-25: 7
Technology assessment, Prep for Sprint 2, Signup and login | 1.5 | 2020-08-24: Search Bar Implementation; 2020-08-25: 2
Created a AWS Account, rokognition and lexa | 0 | 2020-08-24: JIRA Updates; 2020-08-25: 2
New York Location Research and Product backlog | 0.5 | 2020-08-24: Navigo testing; 2020-08-25: 0
GitHub | 0.5 | 2020-08-24: Github; 2020-08-25: 1
Presentation for deliverable 2 | 0 | 2020-08-24: Sprint 2 PPT; 2020-08-25: 3
Brainstroming on database | 1 | 2020-08-24: Brainstorm on Sprint 3; 2020-08-25: 1
Peer to Peer 2 Review | 1 | 2020-08-24: Peer to Peer 2 Review; 2020-08-25: 1
Feedback | 2 | 2020-08-24: Feedback; 2020-08-25: 8
Sprint2 | 4.5 | 2020-08-24: Sprint2
Research on Technical[IEEE] paper and studying formats | 0.5 | 2020-08-24: Tech Paper research/updates; 2020-08-25: 1
Researched and Added Literature review | 0 | 2020-08-24: Sprint 3 updates; 2020-08-25: 0.5
Abstract, Introduction, added Project Requirement | 0.5 | 2020-08-24: JIRA updates; 2020-08-25: 1
Database Schema/Documentation format | 0 | 2020-08-24: Github; 2020-08-25: 0
System Diagrams, ER Diagrams, Data Modeling | 0 | 2020-08-24: Manual Testing; 2020-08-25: 0
Conclusion, Discussion, Summary and References | 1 | 2020-08-24: Database Connectivity; 2020-08-25: 0
Submission of deliverable 3[Technical paper] | 0.25 | 2020-08-24: Submission of Deliverable 3; 2020-08-25: 0.25
brainstorm/coding - Home Page | 0.5 | 2020-08-24: Brainstorm on Sprint 4; 2020-08-25: 2
Peer to Peer 3 Review | 1 | 2020-08-24: Peer to Peer 3 Review; 2020-08-25: 1
Feedback | 2.5 | 2020-08-24: Feedback; 2020-08-25: 1
Sprint 3 | 4.5 | 2020-08-24: Sprint 3; 2020-08-25: 8
Product backlog/Documentation update | 1.5 | 2020-08-24: Designing and Implementing NavigoMerch store; 2020-08-25: 3
Wiki page: Code, Techhnology tools and Project Management | 0.5 | 2020-08-24: Coding- Merch Store; 2020-08-25: 4
Wiki page: Architecture and Design, Burndown Charts, Demo | 0 | 2020-08-24: Architecture/Design; 2020-08-25: 1
coding - Home Page, About Us, Contact | 0 | 2020-08-24: Github; 2020-08-25: 1
coding - User Signup and Login | 0 | 2020-08-24: Final JIRA Updates; 2020-08-25: 0.25
Manual Testing | 0 | 2020-08-24: Manual Testing; 2020-08-25: 0.5
Draft document on design and technologies | 0 | 2020-08-24: Sprint 4 PPT; 2020-08-25: 5
Sprint 4 documentation | 2 | 2020-08-24: Final Documentation; 2020-08-25: 2
Retrospective documentation/mvp | 1 | 2020-08-24: Final Retro; 2020-08-25: 1
Peer to Peer 4 Review | 1 | 2020-08-24: Peer to Peer 4 Review
Feedback | 3 | 2020-08-24: Feedback; 2020-08-25: 1
Sprint 4 | 5 | 2020-08-24: Sprint 4

## Sprint 2 - Burndown Chart
CS 692: Navigo - Sprint 2 - Burndown Chart
Tasks | Working Hours | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-07 | 2020-09-10 | 2020-09-13 | 2020-09-16 | 2020-09-19 | 2020-09-22 | 2020-09-25 | End Hours
Search bar implementation, Prep for Sprint 2 | 10 | 1 | 2 | 1 | 0.5 | 0 | 1 | 0 | 1.5 | 1 | 0 | 8
JIRA Updates | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Web Application Testing | 0 | 1 | 1 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 3.5
GitHub | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4
Presentation for deliverable 2 | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 3
Brainstroming on Sprint 3 | 6 | 0.5 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 8.5
Peer to Peer 2 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
Actual Remaining Hours | 22 | 18.5 | 14.5 | 11.5 | 9.5 | 6.5 | 1.5 | -0.5 | -5 | -7 | -8
Estimated Remaining hours | 22 | 18.9 | 15.8 | 12.7 | 9.6 | 6.5 | 3.4 | 0.3 | -2.8 | -5.9 | -9

## Sprint 3 - Burndown Chart
CS 692: Navigo - Sprint 3 - Burndown Chart
Tasks | Working Hours | 2020-09-27 | 2020-10-01 | 2020-10-03 | 2020-10-05 | 2020-10-08 | 2020-10-10 | 2020-10-12 | 2020-10-16 | 2020-10-17 | 2020-10-18 | End Hours
Tech paper updates/research | 3 | 1 | 0.5 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 3
Sprint 3 updates | 3 | 0.5 | 0.5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3
JIRA Updates | 1.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 1.5
Github updates | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2
Manual Testing | 2 | 0 | 0.5 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
Database updates | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
Submission of deliverable 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 1.5
Brainstorming on Sprint 4 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5 | 0 | 0 | 5.5
Peer to Peer 3 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Actual Remaining Hours | 21.5 | 19.5 | 16.5 | 14 | 12 | 8 | 6 | 3.5 | 1 | 0 | 0
Estimated Remaining hours | 21.5 | 19.35 | 17.2 | 15.05 | 12.9 | 10.75 | 8.6 | 6.45 | 4.3 | 2.15 | 0

## Sprint 4 - Burndown Chart
CS 692: Navigo - Sprint 4 - Burndown Chart
Tasks | Working Hours | 2020-11-05 | 2020-11-08 | 2020-11-10 | 2020-11-14 | 2020-11-20 | 2020-11-24 | 2020-11-28 | 2020-11-30 | 2020-12-02 | 2020-12-04 | End Hours
Designing and Implementing NavigoMerch Store | 5.5 | 1 | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5
Coding: NavigoStore: Sign up, Contact Us, FAQ, DB, Order, Shop, Account management. | 5 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 5
Architecture and Design | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
Github Updates | 12 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 12
JIRA Updates | 12.5 | 1 | 1 | 1 | 2 | 0.5 | 3 | 2 | 2 | 0 | 0 | 12.5
Manual Testing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Sprint 4 updates | 5 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 5
Sprint 4 documentation/submission | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 0 | 0 | 6
Final Retrospective | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2
Peer to Peer 4 Review | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Actual Remaining Hours | 52 | 50 | 45 | 39.5 | 35.5 | 28 | 20.5 | 12 | 1 | 1 | 0
Estimated Remaining hours | 52 | 46.8 | 41.6 | 36.4 | 31.2 | 26 | 20.8 | 15.6 | 10.4 | 5.2 | 0